## Sheet1
Quad Solver
Overview: The Quad Solver is designed to take three double values from the user and return the formulated value(s). The actor, user, inputs the three values into the Quad Solver function and in return recieves the final values.
Date | Task | Assigned to | Time Estimate | Risk 1-10 | Time Taken | % Complete | Feedback
2020-02-24 | Set up files and github. Fill out readme and summary files. | All members | 1 Hour | 1 | 30 min | 100%
2020-03-06 | System platform setup | All members |  | 3 | 30 min | 25% | Decided which development platforms to use
| Total design breakdown into more specific tasks | All members
2020-03-15 | Design tests for input validations
Design user input functionality
Design tests for solving equation step
Design tests for correct answer display to user and reprompt for program repeat
Update github files